## 00_ReadMe
📘 PQC Migration Master Workbook – Usage Guidelines
🎯 Purpose:
This workbook is designed to support the national or organisational effort in migrating from traditional cryptographic algorithms to post-quantum cryptography (PQC), in line with NIST standards.
📂 Sheet Overview & Usage Steps:
1. Table 0 – Initial Inventory:
- Identify cryptographic assets including hardware, firmware, operating systems, and applications.
- Determine readiness and required actions.
2. Table 1 – SBOM (Software Bill of Materials):
- List software components and identify use of cryptographic libraries.
- Link to corresponding CBOM entries.
3. Table 2 – CBOM (Cryptographic Bill of Materials):
- Document cryptographic algorithms, key lengths, libraries, and purpose.
- Suggest PQC replacements based on NIST standards.
4. Table 3 – Risk Register
- Identify risk related PQC migration
5. Table 4 – Risk & Dependency Assessment:
- Assess risk if system remains with quantum-vulnerable algorithms.
- Identify internal/external dependencies and migration barriers.
6. Table 5 – PQC Risk Scoring Matrix:
- Assign Impact (1–5) and Likelihood (1–5) to each system.
- Skor Risiko = Impact × Likelihood.
- Refer to matrix for prioritising migration.
7. Table 6 - Protocol Cryptographic Mapping
- Map cryptographic usage in protocols: function, algorithm, key size, related RFCs/documents.
📊 Risk Interpretation:
- Score 1–4: Risiko Sangat Rendah
- Score 5–9: Risiko Rendah
- Score 10–14: Risiko Sederhana
- Score 15–19: Risiko Tinggi
- Score 20–25: Risiko Sangat Tinggi
🧭 Recommended Workflow:
1. Start with Inventory (Table 0)
2. Proceed to SBOM and CBOM (Tables 1 & 2)
3. Identify Risk Related PQC Migration (Risk Register)(Table 3)
4. Conduct Risk Assessment (Table 4)
5. Calculate Risk Scores (Table 5)
6. Build your migration roadmap

## 0_Inventory
Table 0 – Initial Inventory for PQC Readiness
This table helps identify all cryptographic-related assets including hardware, firmware, operating systems, applications, and services. It is the first step before SBOM and CBOM analysis.
# | Asset Type | Asset Name / Identifier | Location / Owner | Cryptographic Functionality Present? | Examples of Algorithms Used | SBOM/CBOM Available? | Migration Readiness Level | Notes / Action Items
EXAMPLE | Hardware (HSM) | Thales HSM Cluster | Data Centre A | Yes | RSA, AES | CBOM | Low | Engage vendor for PQC roadmap
| Firmware | IoT Sensor Firmware v1.0 | Lab B - SmartSensor | Yes | SHA-256, RSA-1024 | No | Very Low | Full crypto audit required
| Operating System | Red Hat Linux 8.4 | Server 01 | Yes | AES, RSA, ECDSA | SBOM | Medium | Collect package-level SBOM
| Hypervisor | VMware ESXi 7.x | Virtualisation Stack | Yes | AES, RSA | No | Low | Check vendor crypto support
| Cloud Services | AWS CloudHSM, KMS | Cloud Infra Team | Yes | AES, RSA, ECDSA | Yes | Medium | Check AWS PQC timeline
| Application Stack | E-mail Gateway (Postfix + OpenSSL) | Network Ops Team | Yes | RSA, SHA-2 | Yes | Medium | Proceed to SBOM & CBOM analysis
| API Gateway | NGINX + Lua plugin | Internal Dev Team | Yes | ECDSA, AES | Yes | Medium | Enable crypto-agility in configuration
| Database | PostgreSQL 14.2 | App DB Server | Yes | AES, RSA | No | Low | Explore PQC-ready extensions
| Backup Appliance | Veeam Backup | DR Site | Yes | AES-256 | No | Low | Check HSM integration options
| Mobile Devices | Staff App (Android/iOS) | Mobile Dev Team | Yes | AES, ECDSA | SBOM | Medium | Collaborate with mobile dev team
# | Asset Type | Asset Name / Identifier | Location / Owner | Cryptographic Functionality Present? | Examples of Algorithms Used | SBOM/CBOM Available? | Migration Readiness Level | Notes / Action Items
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111

## 1_SBOM
Table 1 – Software Bill of Materials (SBOM)
This table lists software components used in systems identified in Table 0, focusing on cryptographic usage within libraries and software packages.
# | System / Application | Purpose / Usage | URL | Services Mode | Target Customer | Software Component | Third-party Modules | External APIs or Services | Critical Level | Data Category | Is the application/system currently in use? | Application/System Developer | Vendor's Name | Does the agency have expertise? | Does the agency have a special budget allocation? | Link to CBOM
EXAMPLE | E-mail Gateway |  |  | Online | G2C | OpenSSL 3.0.2, Log4j 2.17.1 | Custom Login Module, Spring Security | Google Maps API, MyIdentity (SSO) | Sangat Tinggi | Sulit | Ya | Vendor |  | Tidak | Ya | CBOM #1
| Internal API Server |  |  |  |  | custom-auth-module.js | 2.3.0 | Internal | Very High | Confidential | Yes |  |  |  |  | CBOM #2
| VPN Server |  |  |  |  | strongSwan | 5.9.1 | strongSwan Project | [7 empty] | CBOM #3
| Identity Management |  |  |  |  | Java Keystore (JKS) | JDK 11 | Oracle / OpenJDK | [7 empty] | CBOM #4
| Document Signing System |  |  |  |  | Adobe Sign SDK | Unknown | Adobe | [7 empty] | CBOM #5
| IoT Sensor Gateway |  |  |  |  | Firmware.bin (C code) | v1.0 | Internal | [7 empty] | CBOM #6
| Blockchain App |  |  |  |  | Hyperledger Fabric | 2.2 | Linux Foundation | [7 empty] | CBOM #7
| Payment Gateway |  |  |  |  | PCI HSM Firmware | v3.0 | Vendor Confidential | [7 empty] | CBOM #8
# | System / Application | Purpose / Usage | URL | Services Mode | Target Customer | Software Component | Third-party Modules | External APIs or Services | Critical Level | Data Category | Is the application/system currently in use? | Application/System Developer | Vendor's Name | Does the agency have expertise? | Does the agency have a special budget allocation? | Link to CBOM
1 | EPF Portal |  |  | Online |  | .Net Core 6 | Devexpress Reporting |  | Sangat Tinggi |  | Ya | Vendor | SSDM | Ya
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201

## 2_CBOM
Table 2 – Cryptographic Bill of Materials (CBOM)
This table provides a detailed view of cryptographic functions, algorithms used, and proposed PQC alternatives for each software component.
# (CBOM) | System / Application | Cryptographic Function | Algorithm Used | Library / Module | Key Length | Purpose / Usage | Crypto-Agility Support
EXAMPLE | E-mail Gateway | Digital Signature | RSA-2048 | OpenSSL | 2048-bit | Email signing (S/MIME) | No
| Internal API Server | Key Exchange | ECDH (secp256r1) | Node.js crypto | 256-bit | TLS handshakes | Partial
| VPN Server | Encryption / Key Exchange | AES-GCM + DH | Libgcrypt | 256-bit | VPN data channel | Yes
| Identity Management | Signature / Key Management | RSA-3072 | BouncyCastle | 3072-bit | User auth | No
| Document Signing System | Digital Signature | ECDSA (P-256) | Adobe SDK | 256-bit | Legal document signing | No
| IoT Sensor Gateway | Firmware Signing | RSA-1024, SHA-256 | Mbed TLS | 1024-bit | Secure boot | No
| Blockchain App | TLS, Signatures, Hash | ECDSA, SHA-256 | Fabric SDK | 256-bit | Block & identity signing | Partial
| Payment Gateway | Encryption & Signature | RSA, AES | HSM Firmware | Mixed | Transaction security | No
# (CBOM) | System / Application | Cryptographic Function | Algorithm Used | Library / Module | Key Length | Purpose / Usage | Crypto-Agility Support
CBOM #1
CBOM #2
CBOM #3
CBOM #4
CBOM #5
CBOM #6
CBOM #7
CBOM #8
CBOM #9
CBOM #10
CBOM #11
CBOM #12
CBOM #13
CBOM #14
CBOM #15
CBOM #16
CBOM #17
CBOM #18
CBOM #19
CBOM #20
CBOM #21
CBOM #22
CBOM #23
CBOM #24
CBOM #25
CBOM #26
CBOM #27
CBOM #28
CBOM #29
CBOM #30
CBOM #31
CBOM #32
CBOM #33
CBOM #34
CBOM #35
CBOM #36
CBOM #37
CBOM #38
CBOM #39
CBOM #40
CBOM #41
CBOM #42
CBOM #43
CBOM #44
CBOM #45
CBOM #46
CBOM #47
CBOM #48
CBOM #49
CBOM #50
CBOM #51
CBOM #52
CBOM #53
CBOM #54
CBOM #55
CBOM #56
CBOM #57
CBOM #58
CBOM #59
CBOM #60
CBOM #61
CBOM #62
CBOM #63
CBOM #64
CBOM #65
CBOM #66
CBOM #67
CBOM #68
CBOM #69
CBOM #70
CBOM #71
CBOM #72
CBOM #73
CBOM #74
CBOM #75
CBOM #76
CBOM #77
CBOM #78
CBOM #79
CBOM #80
CBOM #81
CBOM #82
CBOM #83
CBOM #84
CBOM #85
CBOM #86
CBOM #87
CBOM #88
CBOM #89
CBOM #90
CBOM #91
CBOM #92
CBOM #93
CBOM #94
CBOM #95
CBOM #96
CBOM #97
CBOM #98
CBOM #99
CBOM #100
CBOM #101
CBOM #102
CBOM #103
CBOM #104
CBOM #105
CBOM #106
CBOM #107
CBOM #108
CBOM #109
CBOM #110
CBOM #111
CBOM #112
CBOM #113
CBOM #114
CBOM #115
CBOM #116
CBOM #117
CBOM #118
CBOM #119
CBOM #120
CBOM #121
CBOM #122
CBOM #123
CBOM #124
CBOM #125
CBOM #126
CBOM #127
CBOM #128
CBOM #129
CBOM #130
CBOM #131
CBOM #132
CBOM #133
CBOM #134
CBOM #135
CBOM #136
CBOM #137
CBOM #138
CBOM #139
CBOM #140
CBOM #141
CBOM #142
CBOM #143
CBOM #144
CBOM #145
CBOM #146
CBOM #147
CBOM #148
CBOM #149
CBOM #150
CBOM #151
CBOM #152
CBOM #153
CBOM #154
CBOM #155
CBOM #156
CBOM #157
CBOM #158
CBOM #159
CBOM #160
CBOM #161
CBOM #162
CBOM #163
CBOM #164
CBOM #165
CBOM #166
CBOM #167
CBOM #168
CBOM #169
CBOM #170
CBOM #171
CBOM #172
CBOM #173
CBOM #174
CBOM #175
CBOM #176
CBOM #177
CBOM #178
CBOM #179
CBOM #180
CBOM #181
CBOM #182
CBOM #183
CBOM #184
CBOM #185
CBOM #186
CBOM #187
CBOM #188
CBOM #189
CBOM #190
CBOM #191
CBOM #192
CBOM #193
CBOM #194
CBOM #195
CBOM #196
CBOM #197
CBOM #198
CBOM #199
CBOM #200
CBOM #201
CBOM #202
CBOM #203
CBOM #204
CBOM #205
CBOM #206
CBOM #207
CBOM #208
CBOM #209
CBOM #210
CBOM #211
CBOM #212

## 3_RiskRegister
Table 3 – Risk Register
This table helps to identify the potential risk related to PQC migration
# | System Name | Type of Asset | Cryptographic Algorithm | Algorithm Usage | Criticality | Risk | Risk Owner
EXAMPLE | Sistem Emel Dalaman |  | RSA-2048, SHA-1 | Digital Signature | Critical | Ketidakserasian Sistem Legacy dengan PQC | DESD
| Sistem ABC |  | RSA, TLS 1.2 | Signature verification | High | Prestasi Sistem Merosot akibat Penggunaan PQC | BPM, TM
Non alignment of legacy system with PQC
System performance drops on use of PQC
# | Nama Sistem/ Perkakasan/Perisian | Jenis Aset Aplikasi/Perkakasan/Perisian | Algoritma Kriptografi | Kegunaan Algoritma Kriptografi | Tahap Kritikal | Risiko | Pemilik Risiko
1 | Name of software / hardware/ | Aplikasi |  | Use of Cryptography algorithm | Criticality Level / threshold | Risk | Risk owner
2 |  | Perisian
3 |  | Perkakasan
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207

## 4_RiskAssessment
Table 4 – Risk & Dependency Assessment:
This table helps assess the potential impact if legacy cryptography remains in use, and the dependencies between systems/components.
# | Nama Sistem/ Perkakasan/Perisian | Cryptographic Algorithm | Risk | Source of Risk | Impact | Likelihood | Risk Score | Risk Level | Existing Controls | Mitigation Plan
EXAMPLE | Sistem Emel Dalaman | RSA-2048, SHA-1 | Ketidakserasian Sistem Legacy dengan PQC | Sistem/aplikasi sedia ada tidak menyokong algoritma PQC | 5 | 5 | 25 | Very High Risk | Penilaian awal keserasian sistem | Ujian integrasi sistem PQC & pelan mitigasi keserasian
| Sistem e-Tanah | RSA, TLS 1.2 | Prestasi Sistem Merosot akibat Penggunaan PQC | Overhead computational lebih tinggi dalam PQC | 2 | 2 | 4 | Very Low Risk | Penilaian prestasi awal | Optimasi algoritma & upgrade infrastruktur jika perlu
| Internal email syste |  | Non alignment of legacy system with PQC | system does not support PQC Algo |  |  |  |  | Initial alignment Review | integration test with PQC system and non-alignment mitigation plan
|  |  | System performance drops on use of PQC | higher overhead computation with PQC |  |  |  |  | Initial performance review | Optimize algo and upgrade infra if required
# | Nama Sistem/ Perkakasan/Perisian | Algoritma Kriptografi | Risiko | Punca Risiko | Impak | Kemungkinan (Likelihood) | Skor Risiko | Risk Level | Kawalan Sedia Ada | Mitigation Plan
1 | EPF Portal |  |  | source of risk | impact |  | Risk score |  | Existing controls
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191

## 5_RiskMatrix
Table 5 – PQC Risk Scoring Matrix:
This matrix quantifies risk based on impact and likelihood of quantum threats. Risk Score = Impact × Likelihood. Priority is based on resulting score.
Impak / Kemungkinan | Sangat Rendah (1) | Rendah (2) | Sederhana (3) | Tinggi (4) | Sangat Tinggi (5) | KEPUTUSAN PENILAIAN RISIKO
Sangat Tinggi (5) | 5 | 10 | 15 | 20 | 25 | 20 - 25 | Risiko Sangat Tinggi | Migrasi segera, audit sistem, gantian algoritma
Tinggi (4) | 4 | 8 | 12 | 16 | 20 | 15 - 19 | Risiko Tinggi | Perancangan migrasi dan pilot ujian PQC
Sederhana (3) | 3 | 6 | 9 | 12 | 15 | 10 - 14 | Risiko Sederhana | Pemantauan berkala dan tindakan mitigasi jangka panjang.
Rendah (2) | 2 | 4 | 6 | 8 | 10 | 5 - 9 | Risiko Rendah | Perlu dipantau dan ditangani jika perlu.
Sangat Rendah (1) | 1 | 2 | 3 | 4 | 5 | 1 - 4 | Risiko Sangat Rendah | Risiko boleh diterima dan kawalan minimum
| Very low | Low | Medium | High | Very High |  | Very High Risk | Immediate migration, audit system, replace algo
[7 empty] | High Risk | Plan migration and do PQC POC
[7 empty] | Med Risk | Periodic monitoring and long-term mitigation actions.
[7 empty] | Low Risk | Needs to be monitored and addressed if necessary.
RUJUKAN
Kemungkinan: Merujuk kepada kemungkinan berlakunya risiko berdasarkan faktor-faktor seperti rekod sejarah, kelemahan yang dikenal pasti, dan kebarangkalian berdasarkan teknologi yang digunakan. | [5 empty] | Likelihood: Refers to the likelihood of a risk occurring based on factors such as historical records, identified vulnerabilities, and probabilities based on the technology used.
1-Sangat Rendah | Kejadian hampir mustahil berlaku. |  |  |  |  | The event is almost impossible to happen.
2-Rendah | Kejadian jarang berlaku. |  |  |  |  | A rare occurrence.
3-Sederhana | Kejadian yang agak berkemungkinan berlaku. |  |  |  |  | An event that is quite likely to happen.
4-Tinggi | Kejadian yang sangat berkemungkinan berlaku. |  |  |  |  | An event that is very likely to happen.
5-Sangat Tinggi | Kejadian yang sangat hampir pasti berlaku dalam masa terdekat. |  |  |  |  | An event that is very likely to happen in the near future.
Impak: Merujuk kepada kesan atau akibat daripada risiko tersebut terhadap organisasi atau aset kritikal seperti keselamatan data, operasi, dan pematuhan.
Impact: Refers to the effect or consequences of the risk on the organization or critical assets such as data security, operations, and compliance
1-Sangat Rendah | Kesan sangat kecil atau tidak memberi impak kepada operasi. | [6 empty] | Very small or no impact on operations.
2-Rendah | Kesan kecil, mungkin menyebabkan sedikit gangguan tetapi tidak mengancam operasi. | [6 empty] | Minor impact, may cause slight disruption but does not threaten operations.
3-Sederhana | Kesan sederhana yang boleh menyebabkan gangguan operasi tetapi boleh diatasi. | [6 empty] | Moderate impact that may cause operational disruption but can be overcome.
4-Tinggi | Kesan besar yang menyebabkan gangguan signifikan dan mungkin merosakkan operasi atau reputasi. | [6 empty] | Major impact that causes significant disruption and may damage operations or reputation
5-Sangat Tinggi | Kesan yang sangat besar, boleh menyebabkan kegagalan operasi kritikal atau kerugian besar. | [6 empty] | Very large impact, can cause critical operational failure or major losses.

## 6_ProtocolCryptoMap
Protocol | Function | Algorithm | Associated Algorithms | Key Type | Naming in Protocol | Key Size / Digest Size (est.) | Dokumen berkaitan
TLS 1.1 | Key Exchange (KE) | RSA | SHA-1, MD5 | Asymmetric | TLS_RSA_WITH_NULL_MD5, TLS_RSA_WITH_NULL_SHA, TLS_RSA_WITH_RC4_128_MD5, TLS_RSA_WITH_RC4_128_SHA, TLS_RSA_WITH_IDEA_CBC_SHA, TLS_RSA_WITH_DES_CBC_SHA, TLS_RSA_WITH_3DES_EDE_CBC_SHA | 1024 bits | https://datatracker.ietf.org/doc/html/rfc4346
| Key Exchange (KE) | DH |  | Asymmetric | DHE_DSS, DHE_RSA, DH_anon | 1024 bits
| Encryption (ENC) | AES |  | Symmetric | AES_128_CBC | 128 bits
| Encryption (ENC) | 3DES |  | Symmetric | 3DES_EDE_CBC | 168 bits
| Encryption (ENC) | IDEA |  | Symmetric | IDEA_CBC | 64 bits
| Encryption (ENC) | RC4 |  | Symmetric | RC4_128 | 128 bits
| Encryption (ENC) | RC2 |  | Symmetric | RC2_CBC_40 | 40 bits
| HMAC | HMAC-SHA1 |  | Symmetric | HMAC_SHA1 | 160 bits
| HMAC | MD5 |  | Symmetric | HMAC_MD5 | 128 bits
| Signatures (SIG) | RSA | SHA-1, MD5 | Asymmetric | TLS_DH_RSA_WITH_DES_CBC_SHA, TLS_DH_RSA_WITH_3DES_EDE_CBC_SHA, TLS_DHE_RSA_WITH_DES_CBC_SHA, TLS_DHE_RSA_WITH_3DES_EDE_CBC_SHA | 36 byte (288 bits)
| Signatures (SIG) | DSS |  | Asymmetric | TLS_DH_DSS_WITH_DES_CBC_SHA, TLS_DH_DSS_WITH_3DES_EDE_CBC_SHA, TLS_DHE_DSS_WITH_DES_CBC_SHA, TLS_DHE_DSS_WITH_3DES_EDE_CBC_SHA | 1024 bits
| Authentication | X.509 Certs |  | Asymmetric | SubjectPublicKeyInfo | Varies
TLS 1.2 | Key Exchange (KE) | RSA |  | Asymmetric | TLS_RSA_WITH_AES_256_GCM_SHA384 | 2048–4096 bits | https://datatracker.ietf.org/doc/html/rfc5246
| Key Exchange (KE) | DH |  | Asymmetric | TLS_DH_RSA_WITH_AES_128_CBC_SHA | 2048 bits
| Key Exchange (KE) | ECDHE |  | Asymmetric | TLS_ECDHE_RSA_WITH_AES_128_GCM_SHA256 | 256 bits
| Key Exchange (KE) | DHE |  | Asymmetric | TLS_DHE_RSA_WITH_AES_128_GCM_SHA256 | 2048 bits
| Encryption (ENC) | AES |  | Symmetric | AES_128_CBC, AES_256_CBC | 128–256 bits
| Encryption (ENC) | RC4 |  | Symmetric | RC4_128 | 128 bits
| Encryption (ENC) | 3DES (S) |  | Symmetric | 3DES_EDE_CBC | 168 bits
| Encryption (ENC) | ChaCha20 |  | Symmetric | ChaCha20-Poly1305 | 256 bits
| MAC | MD5 |  | Symmetric | HMAC_MD5 | 128 bits
| MAC | HMAC-SHA |  | Symmetric | HMAC_SHA1 | 160 bits
| MAC | HMAC-SHA256 |  | Symmetric | HMAC_SHA256 | 256 bits
| Signatures (SIG) | RSA |  | Asymmetric | RSA-SHA256 | 2048–4096 bits | https://datatracker.ietf.org/doc/html/rfc5246
| Signatures (SIG) | ECDSA |  | Asymmetric | ECDSA-SHA256 | 256 bits | https://datatracker.ietf.org/doc/html/rfc5246
| Authentication | X.509 Certs |  | Asymmetric | Certificate field | Varies | https://datatracker.ietf.org/doc/html/rfc5280
TLS 1.3 | Key Exchange (KE) | ECDHE | P-256, P-384, P-521 | Asymmetric | TLS_AES_128_GCM_SHA256 | 256 bits
| Encryption (ENC) | AES-GCM |  | Symmetric | TLS_AES_128_GCM_SHA256 | 128–256 bits | https://datatracker.ietf.org/doc/html/rfc8446#section-6.3
| Encryption (ENC) | ChaCha20-Poly1305 |  | Symmetric | TLS_CHACHA20_POLY1305_SHA256 | 256 bits | https://datatracker.ietf.org/doc/html/rfc8439
| MAC | Poly1305 (with ChaCha20) |  | Symmetric | CHACHA20_POLY1305 | 256 bits
| Signatures (SIG) | RSA-PSS | SHA-256, SHA-384, SHA-512 | Asymmetric | rsa_pss_rsae_sha256 | 2048–4096 bits
| Signatures (SIG) | ECDSA | SHA-256, SHA-384 or SHA-512 | Asymmetric | ecdsa_secp256r1_sha256 | 256 bits
| Authentication | X.509 Certs |  | Asymmetric | subjectPublicKeyInfo | Varies
IPSec | Key Exchange (KE) | DH/ECDH (A) |  | Asymmetric | ESP/AH headers: Encryption Algorithm, Integrity Algorithm, DH Group | 2048 bits
| Encryption (ENC) | AES (S) |  | Symmetric | ESP/AH headers: Encryption Algorithm, Integrity Algorithm, DH Group | 128–256 bits
| Encryption (ENC) | 3DES (S) |  | Symmetric | ESP/AH headers: Encryption Algorithm, Integrity Algorithm, DH Group | 168 bits | https://datatracker.ietf.org/doc/html/rfc6071
| Integrity / MAC (MAC/INT) | HMAC-SHA1/2 (S) |  | Symmetric | ESP/AH headers: Encryption Algorithm, Integrity Algorithm, DH Group | Depends on hash (e.g., 256 bits for SHA-256)
| Authentication (AUTH) | RSA certs (A) |  | Asymmetric | ESP/AH headers: Encryption Algorithm, Integrity Algorithm, DH Group | 2048–4096 bits
| Authentication (AUTH) | PSK (S) |  | Symmetric | ESP/AH headers: Encryption Algorithm, Integrity Algorithm, DH Group | 128–256 bits
SSH | Key Exchange (KE) | DH/ECDH (A) |  | Asymmetric | kex, cipher, mac, hostkey | 2048 bits
| Encryption (ENC) | AES (S) | AES-128 , AES 256 | Symmetric | kex, cipher, mac, hostkey | 128–256 bits | https://datatracker.ietf.org/doc/html/rfc6668
| Encryption (ENC) | ChaCha20 (S) | ChaCha20-poly1305 | Symmetric | kex, cipher, mac, hostkey | 256 bits | RFC 8439 - ChaCha20 and Poly1305 for IETF Protocols
| Integrity / MAC (MAC/INT) | HMAC (S) | SHA-256 , SHA-512 | Symmetric | kex, cipher, mac, hostkey | Depends on hash (e.g., 256 bits for SHA-256) | RFC 6668 - SHA-2 Data Integrity Verification for the Secure Shell (SSH) Transport Layer Protocol
| Signatures (SIG) | RSA (A) |  | Asymmetric | kex, cipher, mac, hostkey | 2048–4096 bits
| Signatures (SIG) | ECDSA (A) | SHA-256, SHA-384 or SHA-512 | Asymmetric | kex, cipher, mac, hostkey | 256 bits | https://nvlpubs.nist.gov/nistpubs/FIPS/NIST.FIPS.186-5.pdf
| Signatures (SIG) | Ed25519 (A) | SHA-512 | Asymmetric | kex, cipher, mac, hostkey | 256 bits
| Authentication (AUTH) | Password (S) |  | Symmetric | kex, cipher, mac, hostkey | Varies / Protocol-defined | thesis.pdf
| Authentication (AUTH) | Pubkey (A) |  | Asymmetric | kex, cipher, mac, hostkey | Varies / Protocol-defined | https://datatracker.ietf.org/doc/html/rfc4252
OpenPGP | Key Exchange (KE) | ElGamal (A) |  | Asymmetric | Public-Key Algorithm, Symmetric Algorithm, Digest Algorithm | 2048 bits | https://datatracker.ietf.org/doc/html/rfc4880
| Key Exchange (KE) | DH (A) |  | Asymmetric | Public-Key Algorithm, Symmetric Algorithm, Digest Algorithm | 2048 bits
| Encryption (ENC) | AES (S) | AES-128, AES-192, AES-256 | Symmetric | Public-Key Algorithm, Symmetric Algorithm, Digest Algorithm | 128–256 bits
| Encryption (ENC) | Camellia (S) | Camellia-128, Camellia-192, Camellia-256 | Symmetric | Public-Key Algorithm, Symmetric Algorithm, Digest Algorithm | 128–256 bits
| Encryption (ENC) | Twofish | Twofish-256 |  |  | 256 bits
| Integrity / MAC (MAC/INT) | HMAC (S) | SHA-2, SHA-3 | Symmetric | Public-Key Algorithm, Symmetric Algorithm, Digest Algorithm | SHA2-224, 256, 384, 512, SHA3-256, 512
| Signatures (SIG) | RSA (A) |  | Asymmetric | Public-Key Algorithm, Symmetric Algorithm, Digest Algorithm | 2048–4096 bits
| Signatures (SIG) | DSA (A) | SHA-256, SHA-384 or SHA-512 | Asymmetric | Public-Key Algorithm, Symmetric Algorithm, Digest Algorithm | 2048 bits
| Signatures (SIG) | ECDSA (A) | SHA-1 | Asymmetric | Public-Key Algorithm, Symmetric Algorithm, Digest Algorithm | 256 bits
| Authentication (AUTH) | Sig verification (A) |  | Asymmetric | Public-Key Algorithm, Symmetric Algorithm, Digest Algorithm | Varies / Protocol-defined | https://datatracker.ietf.org/doc/html/rfc4880
S/MIME | Encryption (ENC) | AES (S) | AES-128,256 GCM, AES-128 CBC | Symmetric | EncryptionAlgorithm, DigestAlgorithm, SignatureAlgorithm | 128,256 bits | https://datatracker.ietf.org/doc/html/rfc8551#section-3.3
| Encryption (ENC) | 3DES (S) |  | Symmetric | EncryptionAlgorithm, DigestAlgorithm, SignatureAlgorithm | 168 bits
| Integrity / MAC (MAC/INT) | SHA2/3 (S usage) |  | Symmetric | EncryptionAlgorithm, DigestAlgorithm, SignatureAlgorithm | Depends on hash (e.g., 256 bits for SHA-256)
| Signatures (SIG) | RSA (A) | SHA-256, SHA-1 | Asymmetric | RSA, RSASSA-PSS, RSAES-OAEP (Key Pair Generation, Signature Generation, Signature Verification, Encryption, Decryption) | 2048 - 4096 bits
| Signatures (SIG) | ECDSA (A) | Curve P-256, SHA-256 | Asymmetric | Signature Generation, Signature Verification | 256 bits
| Authentication (AUTH) | X.509 certs (A) |  | Asymmetric | SMIMEEncryptionKeyPreference (Selection of Recipient Key Management Certificate) | Varies / Protocol-defined
Signal | Key Exchange (KE) | X3DH: Curve25519 (A) |  | Asymmetric | X3DH, AES256_CTR, HMAC_SHA256, Curve25519 | 2048 bits | https://medium.com/@janelle.wg/demystifying-the-signal-protocol-for-end-to-end-encryption-c93250e6043e
| Encryption (ENC) | AES-CTR (S) |  | Symmetric | X3DH, AES256_CTR, HMAC_SHA256, Curve25519 | 128–256 bits
| Integrity / MAC (MAC/INT) | HMAC-SHA256 (S) |  | Symmetric | X3DH, AES256_CTR, HMAC_SHA256, Curve25519 | Depends on hash (e.g., 256 bits for SHA-256)
| Authentication (AUTH) | Identity keys Curve25519 (A) |  | Mixed | Curve25519 | 256 bits | https://medium.com/@janelle.wg/demystifying-the-signal-protocol-for-end-to-end-encryption-c93250e6043e
Kerberos | Encryption (ENC) | AES (S) | AES 128-bit and AES 256-bit | Symmetric | AES256, AES128 | 128–256 bits | https://learn.microsoft.com/en-us/previous-versions/windows/it-pro/windows-10/security/threat-protection/security-policy-settings/network-security-configure-encryption-types-allowed-for-kerberos
| Encryption (ENC) | DES (S) |  | Symmetric | DES_CBC | 56 bits | RFC 4120
| Encryption (ENC) | 3DES (S) |  | Symmetric | DES3-KD, DES3-CBC | 192 bits | RFC 4120
| Encryption (ENC) | HMAC_MD5 | RSA | Symmetric | MD5 | 128 bits | RFC 4120
| Integrity / MAC (MAC/INT) | HMAC-SHA1 (S) |  | Symmetric | HMAC_SHA1_96 | 96 bits | RFC 4120
| Authentication (AUTH) | Tickets/password-derived keys (S); PKINIT certs (A optional) |  | Mixed (S core) | etype, ticket, authenticator | Varies / Protocol-defined | https://datatracker.ietf.org/doc/html/rfc8636
WireGuard | Key Exchange (KE) | Curve25519 (A) |  | Asymmetric | Key Exchange | 256 bits | https://datatracker.ietf.org/doc/html/rfc7748
| Encryption (ENC) | ChaCha20 (S) | Poly1305 | Symmetric | noise protocol, peer public key, handshake | 256 bits | WireGuard: Next Generation Kernel Network Tunnel
| Integrity / MAC (MAC/INT) | Poly1305 (S) |  | Symmetric | noise protocol, peer public key, handshake | 256 bits
| Authentication (AUTH) | Static public keys (A) | Curve25519 | Asymmetric | Authentication | 256-bits | https://datatracker.ietf.org/doc/html/rfc7748
Zigbee | Encryption (ENC) | AES-CCM (S) | CBC-MAC | Symmetric | AES-CCM*, MIC, Key Transport | 128–256 bits | ZigBee Security: Basics (Part 2) – Kudelski Security Research
| Integrity / MAC (MAC/INT) | AES-CCM MIC (S) | AES‑CCM | Symmetric | AES-CCM*, MIC, Key Transport | 128–256 bits | AN1233: Zigbee Security
| Authentication (AUTH) | Network/Link keys (S) | AES‑CTR | Symmetric | AES-CCM*, MIC, Key Transport | Varies / Protocol-defined
WPA2 / WPA3 | Key Exchange (KE) | SAE (A-style) |  | Asymmetric | SAE, CCMP, PMK, PTK, GTK | 256 bits | https://www.wi-fi.org/system/files/WPA3%20Specification%20v3.4.pdf , https://datatracker.ietf.org/doc/html/rfc7664
| Key Exchange (KE) | PSK (S) | HMAC-SHA1 | Symmetric | SAE, CCMP, PMK, PTK, GTK | 128–256 bits | https://standards.ieee.org/ieee/802.11i/3127
| Encryption (ENC) | AES-CCMP (S) |  | Symmetric | SAE, CCMP, PMK, PTK, GTK | 128–256 bits | https://datatracker.ietf.org/doc/html/rfc4309
| Integrity / MAC (MAC/INT) | HMAC-SHA256 (S) | HMAC-SHA256, SAE | Symmetric | SAE, CCMP, PMK, PTK, GTK | Depends on hash (e.g., 256 bits for SHA-256) | IEEE 802.11w, IEEE 802.11-2016/2020
| Authentication (AUTH) | Passphrase/PSK (S) |  | Symmetric | SAE, CCMP, PMK, PTK, GTK | 128–256 bits
| Authentication (AUTH) | SAE creds (A-PAKE) |  | Asymmetric | SAE, CCMP, PMK, PTK, GTK | 256 bits | https://www.wi-fi.org/system/files/WPA3%20Specification%20v3.4.pdf , https://datatracker.ietf.org/doc/html/rfc7664
DNSSEC | Signatures (SIG) | RSA (A) |  | Asymmetric | RRSIG, DNSKEY, DS, NSEC | 2048–4096 bits
| Signatures (SIG) | ECDSA (A) | P-256 and SHA-256, and ECDSA with curve P-384 and SHA-384 | Asymmetric | RRSIG, DNSKEY, DS, NSEC | 256 bits | https://datatracker.ietf.org/doc/html/rfc6605
| Signatures (SIG) | EdDSA (A) | SHAKE-256 | Asymmetric | RRSIG, DNSKEY, DS, NSEC | 256 bits | https://datatracker.ietf.org/doc/html/rfc8080#section-6.2
| Authentication (AUTH) | DNSKEY/RRSIG validation (A) |  | Asymmetric | RRSIG, DNSKEY, DS, NSEC | Varies / Protocol-defined | https://datatracker.ietf.org/doc/html/rfc4034
QUIC (TLS 1.3) | Key Exchange (KE) | ECDHE (A) |  | Mixed | inherits TLS naming (e.g., TLS_AES_128_GCM_SHA256) | 2048 bits
| Encryption (ENC) | AES-GCM (S) | AEAD, used in TLS 1.3 | Symmetric | inherits TLS naming (e.g., TLS_AES_128_GCM_SHA256) | 128–256 bits | [2405.09264] A Quantum of QUIC: Dissecting Cryptography with Post-Quantum Insights
| Encryption (ENC) | ChaCha20-Poly1305 (S) | AEAD, for low-power devices | Symmetric | inherits TLS naming (e.g., TLS_AES_128_GCM_SHA256) | 256 bits | https://datatracker.ietf.org/doc/html/rfc8446
| Integrity / MAC (MAC/INT) | AEAD tags (S) |  | Symmetric | inherits TLS naming (e.g., TLS_AES_128_GCM_SHA256) | Varies / Protocol-defined
| Signatures (SIG) | RSA (A) |  | Mixed | inherits TLS naming (e.g., TLS_AES_128_GCM_SHA256) | 2048–4096 bits
| Signatures (SIG) | ECDSA (A) |  | Mixed | inherits TLS naming (e.g., TLS_AES_128_GCM_SHA256) | 256 bits
| Authentication (AUTH) | Certs (A) |  | Mixed | inherits TLS naming (e.g., TLS_AES_128_GCM_SHA256) | Varies / Protocol-defined
Bitcoin | Signatures (SIG) | ECDSA (A) | secp256k1 | Asymmetric | pubkey, scriptPubKey, sigHash | 256 bits | https://datatracker.ietf.org/doc/html/rfc6090
| Authentication (AUTH) | Ownership via signs (A) | secp256k1 | Asymmetric | pubkey, scriptPubKey, sigHash | Varies / Protocol-defined
Tor | Key Exchange (KE) | DH (A) | Curve25519 | Asymmetric | create cell, relay cell, onion | 2048 bits | https://datatracker.ietf.org/doc/html/rfc3526
| Key Exchange (KE) | RSA (A) | RSAES-PKCS1-v1_5, RSASSA-PKCS1-v1_5 | Asymmetric | create cell, relay cell, onion | 2048–4096 bits | https://datatracker.ietf.org/doc/html/rfc8017
| Encryption (ENC) | AES (S) | AES-128 CTR | Symmetric | create cell, relay cell, onion | 128–256 bits | https://datatracker.ietf.org/doc/html/rfc3268
| Integrity / MAC (MAC/INT) | SHA1 digest / TLS MACs (S usage) | HMAC-SHA1 | Symmetric | create cell, relay cell, onion | Varies / Protocol-defined | https://datatracker.ietf.org/doc/html/rfc5246
| Authentication (AUTH) | Onion handshake keys (A) |  | Mixed | create cell, relay cell, onion | Varies / Protocol-defined
iMessage | Key Exchange (KE) | Curve25519 (A) | X25519 | Mixed | key bags, envelope encryption | 256 bits | https://datatracker.ietf.org/doc/html/rfc7748
| Encryption (ENC) | AES (S) | AES-GCM | Symmetric | key bags, envelope encryption | 128–256 bits
| Integrity / MAC (MAC/INT) | HMAC (S) | HMAC-SHA256 | Symmetric | key bags, envelope encryption | Depends on hash (e.g., 256 bits for SHA-256) | https://datatracker.ietf.org/doc/html/rfc2104
| Authentication (AUTH) | Apple ID cert chain (A) | RSA, ECDSA | Mixed | key bags, envelope encryption | Varies / Protocol-defined
OAuth / OIDC | Integrity / MAC (MAC/INT) | HMAC (S; JWT HS256) |  | Symmetric | JWT, id_token, access_token | Depends on hash (e.g., 256 bits for SHA-256) | https://datatracker.ietf.org/doc/html/rfc7519#section-7.1
| Signatures (SIG) | RSA (A) | RS256, RS384, RS512 | Mixed | JWT, id_token, access_token | 2048–4096 bits | https://datatracker.ietf.org/doc/html/rfc7518
| Signatures (SIG) | ECDSA (A) | ES256, ES384, ES512 | Mixed | JWT, id_token, access_token | 256 bits | https://datatracker.ietf.org/doc/html/rfc7518
| Signatures (SIG) | EdDSA (A) | Ed25519, Ed448 | Mixed | JWT, id_token, access_token | 256 bits | https://datatracker.ietf.org/doc/html/rfc8037
| Signatures (SIG) | HMAC (S) | HS256, HS384, HS512 | Symmetric | JWT, id_token, access_token | Depends on hash (e.g., 256 bits for SHA-256) | https://datatracker.ietf.org/doc/html/rfc7518
| Authentication (AUTH) | Tokens: client secret (S) or JWK (A) |  | Mixed | JWT, id_token, access_token | Varies / Protocol-defined | https://datatracker.ietf.org/doc/html/rfc6749
FIDO2 / WebAuthn | Integrity / MAC (MAC/INT) | Hash (S usage) |  | Asymmetric | attestation, assertion, credID | Varies / Protocol-defined | https://developers.yubico.com/python-fido2/API_Documentation/autoapi/fido2/webauthn/index.html
| Signatures (SIG) | ECDSA (A) | ECDSA secp256k1 SHA-256 | Asymmetric | ES256 | 256 bits | https://datatracker.ietf.org/doc/html/draft-ietf-cose-webauthn-algorithms-01
| Signatures (SIG) | EdDSA (A) |  | Asymmetric | attestation, assertion, credID | 256 bits | https://developers.yubico.com/WebAuthn/Concepts/Using_WebAuthn_for_Signing.html
| Authentication (AUTH) | Public-key assertions (A) |  | Asymmetric | attestation, assertion, credID | Varies / Protocol-defined | https://en.wikipedia.org/wiki/WebAuthn
MACsec | Encryption (ENC) | AES-GCM (S) |  | Symmetric | SAK, SCI, PN, SecTAG | 128–256 bits | https://ieeexplore.ieee.org/abstract/document/9044731
| Integrity / MAC (MAC/INT) | AES-GCM tag (S) |  | Symmetric | SAK, SCI, PN, SecTAG | 128–256 bits | https://ieeexplore.ieee.org/abstract/document/9044731
| Authentication (AUTH) | PSK / 802.1X creds (S/A depending backend) |  | Symmetric | SAK, SCI, PN, SecTAG | 128–256 bits | https://info.support.huawei.com/info-finder/encyclopedia/en/MACsec.html
OpenVPN | Key Exchange (KE) | DH/ECDH (A) |  | Asymmetric | TLS-auth, cipher, auth, key-direction | 2048 bits | https://datatracker.ietf.org/doc/html/rfc2409, https://datatracker.ietf.org/doc/html/rfc8422
| Key Exchange (KE) | RSA (A) | easy-rsa | Asymmetric | TLS-auth, cipher, auth, key-direction | 1024 bits | https://openvpn.net/community-docs/setting-up-your-own-certificate-authority--ca--and-generating-certificates-and-keys-for-an-openvpn-server-and-multiple-clients.html
| Encryption (ENC) | AES (S) | CBC/GCM/HMAC-SHA256 | Symmetric | TLS-auth, cipher, auth, key-direction | 128–256 bits | NIST SP 800-38, RFC2104
| Encryption (ENC) | Camellia (S) | HMAC-SHA1 or HMAC-SHA256 | Symmetric | TLS-auth, cipher, auth, key-direction | 128–256 bits | RFC6367
| Integrity / MAC (MAC/INT) | HMAC (S) | SHA-1/SHA-256/SHA-512 | Symmetric | TLS-auth, cipher, auth, key-direction | Depends on hash (e.g., 256 bits for SHA-256) | RFC3174, RFC 6234
| Signatures (SIG) | MD5 | md5WithRSAEncryption |  |  |  | https://openvpn.net/connect-docs/md5-signature-algorithm-support.html
| Authentication (AUTH) | Static key (S) or TLS certs (A) or HMAC using SHA1 |  | Mixed | TLS-auth, cipher, auth, key-direction | Varies / Protocol-defined | https://openvpn.net/community-resources/reference-manual-for-openvpn-2-4/
DTLS | Key Exchange (KE) | (EC)DHE/RSA (A) |  | Mixed | DTLS-SRTP keying, cipher suite, MAC | 2048–4096 bits | https://www.redhat.com/en/blog/understanding-dtls-all-zero-clienthellorandom-vulnerability#:~:text=Figure%201:%20DTLS%201.2%20handshake,also%20use%20the%20random%20nonces:
| Encryption (ENC) | ChaCha20 (S) | Poly1305 | Symmetric |  | 128-256 | RFC 9147
| Encryption (ENC) | AES(S) | AES-GCM, AES-CCM | Symmetric | DTLS-SRTP keying, cipher suite, MAC | 128–256 bits | RFC 9147
| Integrity / MAC (MAC/INT) | HMAC/Poly1305 (S) | ChaCha20 | Symmetric | DTLS-SRTP keying, cipher suite, MAC | Depends on hash (e.g., 256 bits for SHA-256) | RFC 9147
| Signatures (SIG) | RSA/ECDSA (A) |  | Mixed | DTLS-SRTP keying, cipher suite, MAC | 32–46 byte | https://www.redhat.com/en/blog/understanding-dtls-all-zero-clienthellorandom-vulnerability#:~:text=Figure%201:%20DTLS%201.2%20handshake,also%20use%20the%20random%20nonces:
| Authentication (AUTH) | Certs/PSK (A/S) | plain PSK, (EC)DHE_PSK, and RSA_PSK | Mixed | DTLS-SRTP keying, cipher suite, MAC | 128–256 bits | https://www.redhat.com/en/blog/understanding-dtls-all-zero-clienthellorandom-vulnerability#:~:text=Figure%201:%20DTLS%201.2%20handshake,also%20use%20the%20random%20nonces:
Note on C133: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If ephemeral Diffie-Hellman (DHE) key exchange or its Elliptic Curve variant (ECDHE) is used, then a shared secret value obtained from the key agreement process is used. If RSA key exchange is used, then a random value generated by the client is used.
Note on G137: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 32-byte long random values for (EC)DHE and 46-byte long values for RSA